## Letter1
Annex 13 (M5.3.4). Full list of measures in the Lower Danube sub-basin
№ | The main water and environmental problem | Subproblem | Event. (according to the Resolution of the Cabinet of Ministers of Ukraine No. 336) | Type of event | Name of the event | Description of the event | Technical description | Entity | Restoring the damage caused by the war | The event is included in the Recovery Plan of Ukraine | Number of people affected by the event | River basin | Sub-basin | Area. | District | Territorial community (TC) | IPR or category of IPR | MPV/MPZV code | Assessment of the risk of not achieving good status of the MHM/MPP | Ecological status of the MWR or quantitative status of the MWR | Chemical state of the MPV or MPZV | Areas to be protected | Unit of measurement | [5 empty] | Number of units | [5 empty] | Cost of investment per unit | Total cost of investment | Unit cost of operation and maintenance | Total cost of operation and maintenance | Total cost of the event | Indicate the date on which the calculations were made in columns 24-28 | Programme. | Sources of funding | Body/organisation responsible for implementation | Implementation period | Priority. | Comments, sources of information | Who proposed the event | When an event is proposed
[9 empty] | Yes / No | Yes / No | thousands of people | [7 empty] | At risk / No risk |  |  |  | thousandm3/day | м3 | km | ha | tonnes | others | thousandm3/day | м3 | km | ha | tonnes | others | million UAH | million UAH | million UAH | million UAH | million UAH |  |  |  |  | years
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | [5 empty] | 24 | [5 empty] | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
MAIN EVENTS
1 | GWEP 4 |  | 8.1.4 |  | Clearing the bed of the Balanesti River Reniiskaya TG Izmail district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Prevention of flooding emergencies in the city of Reni by clearing the 12.6 km long Balanesti gully. Google coordinates of the restoration area are from 45.435512, 28.322930 to 45.506244, 28.247245 | Reni TG | no |  | 36.1 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Reni TG | Danube River | UA_M5.3.4_0001 | At risk | Failure to achieve the good |  | missing |  |  | + | [5 empty] | 12.6 |  |  |  | 2.5 | 31.5 |  |  | 31.5 | 2022 | The EU Strategy for the Danube Region | Regional and local budgets, other funds not prohibited by law | Reni TG | 2025-2031 | 1 | No design project, estimates are approximate |  | 2023
2 | GWEP 4 |  | 8.1.4 |  | Rehabilitation of the former oil storage facility and prevention of oil pollution in the border area Reniiska TG Izmail district, Odesa region | Implementation of a set of measures to prevent oil pollution of the Danube River bank (development of the project design) | The area of contamination is approximately 0.35 hectares. The volume of contamination is approximately 6.5 thousand m³ of soil. Google coordinates of the remediation site: 45.385582, 28.299288 | Reni TG | no |  | 36.1 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Reni TG | Danube River | UA_M5.3.4_0001 | At risk | Failure to achieve the good |  | missing |  |  |  | + | [5 empty] | 0.35 |  |  | 1.2 | 0.42 |  |  | 0.42 | 2022 | The EU Strategy for the Danube Region | Regional and local budgets, other funds not prohibited by law | Reni TG | 2025-2031 | 1 | No design project, estimates are approximate |  | 2023
3 | GWEP 4 |  | 8.1.4 |  | Creation of wastewater treatment and solid waste disposal complexes in the waters of the Danube seaports 5TG Izmail district, Odesa region | Creation of a complex for the treatment of bilge and other oily waste, heat treatment of special shipboard waste incinerators, using the collected oil products as fuel for incinerators. | Development and use of specialised port infrastructure, superstructures and technical base of relevant facilities and equipment. Creation of a complex for the treatment of bilge and other oily waste, and thermal treatment of special ship waste incinerators, using the collected oil products as fuel for incinerators. Launching a special vessel (for waste treatment) to sail in the general sector of the Danube | Reniyska TG Safianivska TG Izmailskaya TG Kiliya TG Vylkivska TG | no |  | 252.5 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Reniyska TG Safianivska TG Izmailskaya TG Kiliya TG Vylkivska TG | Danube River | UA_M5.3.4_0001 UA_M5.3.4_0002 UA_M5.3.4_0003 | At risk | Недосягнення доброго UA_M5.3.4_0001 UA_M5.3.4_0003 |  | Danube Biosphere Reserve of national importance | [5 empty] | + | [7 empty] | 4.2 |  |  | 4.2 | 2022 | The EU Strategy for the Danube Region | Regional and local budgets, other funds not prohibited by law | Reniyska TG Safianivska TG Izmailskaya TG Kiliya TG Vylkivska TG | 2025-2031 | 1 | No design project, estimates are approximate |  | 2023
4 | GWP 1, GWP 2, GWP 3, GWP 4 |  | 8.1.1, 8.1.2, 8.1.3, 8.1.4 |  | Establishment of water protection zones and coastal protection strips for water bodies in 16 TGs in Bilhorod-Dnistrovskyi rayon, Bolhradskyi rayon, Izmailskyi rayon Odesa oblast | Establishment of coastal protection strips of water bodies and water protection zones in accordance with Article 87, Article 88 of the Water Code of Ukraine. Determining the boundaries of water protection zones (WPZ), coastal protection strips (CPZ), beach zones (BZ) and floodplains of small rivers (FPR), indicating them in land management documentation, urban planning documentation at the local and regional level, entering information on the relevant restrictions on land use into the State Land Cadastre (SLC) and marking these boundaries on the ground with information signs. | Establishment of coastal protection strips and water protection zones in comprehensive plans for the spatial development of territories of territorial communities, master plans of settlements, or by amending master plans of settlements. Indication of the boundaries of coastal protection strips and water protection zones in land management and urban planning documentation and marking them on the ground with information signs. Determination of the boundaries of water protection zones in land management projects for the organisation and establishment of the boundaries of territories of the nature reserve fund and other environmental protection, health, recreational, historical, cultural, forestry, water fund lands and water protection zones, restrictions on the use of land and their regime-forming objects. Entering information on the boundaries of coastal protection strips and water protection zones into the State Land Cadastre as information on restrictions on land use. | Territorial communities | no |  | 0 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bilhorod-Dnistrovskyi, Bolgradskyi, Izmailskyi | Tatarbunary TG, Krynychne TG, Vasylivka TG, Pavlivka TG, Bolhrad TG, Artsyz TG, Tarutino TG, Teplyk TG, Kubey TG, Horodnya TG, Vilkovo TG, Suvorove TG, Safianivka TG, Reni TG, Kiliya TG, Izmail TG | Danube River, Kislicki arm, Ivanesti arm, Tataru mouth, Stepovyi arm, Katenka arm, Mashenka arm, Laptish mouth, Murza mouth, Solomonov arm, Belgorodske mouth, Ochakivske mouth, Prorva mouth, IZMV No name, IZMV No name, Viketa stream, IZMV connecting channel of Lake Kart. Kart, Yalpukh River, Bolshaya Salcha River, Skunda River, Karasulak River, Kugu Lake IWRM connecting channel, Kairakliya River, Kairakliya Lake IWRM connecting channel, Lung Lake IWRM connecting channel. Lung, Tashbunar River, Bolshoy Katlabukh River, Bolshoy Katlabukh River, Maly Katlabukh River, Maly Katlabukh River, Yenika River, Yenika River, Zhelyavsky Connecting Canal, Kirgiz-China River, Kirgiz-China River, No name, Valeperzha river, Valeperzha river, Kirgiz river, Kirgiz river, Kirgiz river, No name, Aliyaga river, Tashlyk river, Tashlyk river, Kofa canal, Drakulya river, Drakulya river, Nerushai river, Nerushai river | UA_M5.3.4_0001, UA_M5.3.4_0002, UA_M5.3.4_0003, UA_M5.3.4_0004, UA_M5.3.4_0005, UA_M5.3.4_0006, UA_M5.3.4_0007, UA_M5.3.4_0008, UA_M5.3.4_0009, UA_M5.3.4_0010, UA_M5.3.4_0011, UA_M5.3.4_0012, UA_M5.3.4_0013, UA_M5.3.4_0014, UA_M5.3.4_0015, UA_M5.3.4_0016, UA_M5.3.4_0017, UA_M5.3.4_0019, UA_M5.3.4_0021, UA_M5.3.4_0022, UA_M5.3.4_0023, UA_M5.3.4_0026, UA_M5.3.4_0027, UA_M5.3.4_0029, UA_M5.3.4_0030, UA_M5.3.4_0031, UA_M5.3.4_0033, UA_M5.3.4_0036, UA_M5.3.4_0037, UA_M5.3.4_0039, UA_M5.3.4_0040, UA_M5.3.4_0042, UA_M5.3.4_0043, UA_M5.3.4_0045, UA_M5.3.4_0046, UA_M5.3.4_0048, UA_M5.3.4_0049, UA_M5.3.4_0050, UA_M5.3.4_0051, UA_M5.3.4_0052, UA_M5.3.4_0054, UA_M5.3.4_0055, UA_M5.3.4_0056, UA_M5.3.4_0057, UA_M5.3.4_0058, UA_M5.3.4_0060, UA_M5.3.4_0062, UA_M5.3.4_0063, UA_M5.3.4_0064, UA_M5.3.4_0066, UA_M5.3.4_0067, UA_M5.3.4_0068, UA_M5.3.4_0069, UA_M5.3.4_0071, UA_M5.3.4_0072, UA_M5.3.4_0074, UA_M5.3.4_0075, UA_M5.3.4_0077, UA_M5.3.4_0078, UA_M5.3.4_0079, UA_M5.3.4_0080, UA_M5.3.4_0081, UA_M5.3.4_0082, UA_M5.3.4_0083, UA_M5.3.4_0085, UA_M5.3.4_0087, UA_M5.3.4_0088, UA_M5.3.4_0090, UA_M5.3.4_0091, UA_M5.3.4_0093 | At risk / Possibly at risk |  | Недосягнення доброго UA_M5.3.4_0001, UA_M5.3.4_0003, UA_M5.3.4_0004, UA_M5.3.4_0012, UA_M5.3.4_0018, UA_M5.3.4_0023, UA_M5.3.4_0029 | Danube Biosphere Reserve of national importance |  |  | + | [5 empty] | 963,1 |  |  |  |  | 6,93 |  |  | 6,93 | 2022 |  | local, state budget, other sources of funding | Local self-government bodies | 2025-2030 | 2 | The design and estimate documentation (DED) has not been developed, the calculations are approximate | The Black Sea and lower Danube rivers | 2022
5 | GWEP 4 |  | 8.1.4 |  | Clearing of the Belgorod Canal and internal ditches in Vilkovo Vilkovo TG Izmail district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); - Improving stream continuity for biota migration, etc. | It is planned to deepen the Belgorod Canal (10.5 km long), with an estimated volume of silt to be removed of 4.75 thousand m3. Cleaning of internal channels (gullies), The measure is aimed at restoring the hydrological and sanitary condition of the canals (eriks). The total length of the channels is 14 km, the estimated volume of silt removed is 21.0 thousand m3 | Vylkivska TG | no |  | 11.45 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Vylkivska TG | Danube River | UA_М5.3.4._0003 | At risk | Failure to achieve the good |  | Danube Biosphere Reserve of national importance |  |  | + | [5 empty] | 24.5 |  |  |  | 0.735 | 18 |  |  | 18 | 2020 р. | Development Strategy of Vilkovo City Council (Territorial Community) for 2019-2025 | State budget | Vylkivska TG | 2025-2030 | 2 | Existing project 2020 Taking into account inflation and price increases, the project cost as of 2023 is approximately UAH 34.0 million. | Vylkivska TG | 2023
6 | GWP 1, GWP 2, GWP 3 |  | 8.1.1., 8.1.2., 8.1.3. |  | Construction of sewage treatment plants and sewerage networks in the city of Kilia Kilia TG Izmail district, Odesa region | General (mandatory) data on the CSP operator: 1. Balance holder: ME "Svitlo" 2. EDRPOU code: 32319458 3. Water user code: 510747 4. Information on the operation of the WSS (as of 01.01.2023) Wastewater discharged per year, million cubic metres - total: 0.1167 - without treatment: 0 - insufficiently treated: 0.1167 - normatively clean (without cleaning): 0 - normatively treated at treatment plants: 0 - biological treatment: 0 - physical and chemical treatment: 0 - mechanical: 0 - capacity of treatment facilities after which waste water is discharged into water bodies: 0.1168 including those that provide regulatory treatment: capacity of treatment facilities, after which the return (waste) water is discharged to irrigation fields, terrain, filtration fields, storage tanks and cesspools: 0 | 1. Number of sewage treatment systems (STS) - actual / plan : 1/1 2. Method of wastewater treatment - actual - MECH (1)/BIO(2) - plan - MECH(1)/BIO(2)/TRO(3) 3. Capacity of facilities after which wastewater is discharged to the surface water body (SWB) - actual - 0.32 thousand m³/day (0.1168 million m³/year) - plan - 5.77 thousand m³/day (2.106 million m³/year) 4. Residual sediment (sludge) - actual - untreated (storage) - plan - treatment (partial processing) 5. Stormwater drainage (SW) - collector-drainage water (rain and meltwater) - fact - mechanical treatment (CD/MEH) - plan - treatment (CD/MECH/BIO) 6. Access to sanitation (connection of the population to the SSS (%) number of subscribers (population) of the territorial community (TC) - actual - 100%/21.637 thousand people - plan - 100%/21.637 thousand people 7. Climate neutrality - actual - use of outdated equipment - plan - replacement of equipment, use of energy-saving pumping equipment | KP Svetlo | No. |  | 21.6 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Kiliya TG | Danube River | UA_M5.3.4_0003 | At risk | Failure to achieve the good |  | Danube Biosphere Reserve of national importance | + | [5 empty] | 5.77 | [5 empty] | 67.5 | 389.466 |  |  | 389,466 | 2022 | The Drinking Water of Ukraine programme, regional and oblast programmes for socio-economic development of the community | State, local budgets, other budgets not prohibited by law | Executive Committee of the Kielce City Council | 2025-2030 | 1 | Working project No. 217 dated 15.08.2017 "Sewage treatment plant in Kiliya, Odesa region" Application of BIOCOS technology (Austria) State budget (as of 30.07.2017, UAH 151.765 million). The project has not been implemented. Therefore, the calculation was made as of 30.07.2017. The calculation is based on the estimated cost of clean-up of BIO - EUR 200 per person, TRO - EUR 250 per person at the NBU exchange rate of UAH 40. Total cost 21,637 x 450 x 40 = UAH 346,140 million | Executive Committee of the Kielce City Council | 2022 рік
7 | GWP 1, GWP 2, GWP 3 |  | 8.1.1., 8.1.2., 8.1.3. |  | Reconstruction of sewage treatment facilities in Izmail, Izmail TG Izmail district, Odesa region | General (mandatory) data about the CSP operator: Balance sheet holder: PJSC "ICCC" 2. EDRPOU code: 00278818 3. Water user code: 510045 4. Information on the operation of the WSS (as of 01.01.2023) Wastewater discharged per year, million cubic metres - total: 1.9745 - without treatment: 0 - insufficiently treated: 0 - normatively clean (without purification): 0.0032 - normatively treated at treatment plants: 0 - biological treatment: 1.9713 - physical and chemical treatment: 0 - mechanical: 0 - capacity of treatment facilities after which waste water is discharged into water bodies: 15.33 including those that provide regulatory treatment: 1.9713 capacity of treatment facilities, after treatment of which return (waste) water is discharged to irrigation fields, terrain, filtration fields, storage tanks and cesspools: 0 | 1. Number of sewage treatment systems (STS) - actual / plan : 1/0 2. Method of wastewater treatment - actual - MECH(1)/BIO(2) - plan - MEH(1)/BIO(2)/TRO(3) 3. Capacity of facilities after which wastewater is discharged to the surface water body (SWB) - actual - 42 thousand m³/day (15.33 million m³/year) - plan - 52.9 thousand m³/day (19.309 million m³/year) 4. Residual sediment (sludge) - actual - untreated (storage) - plan - treatment (partial processing) 5. Stormwater drainage (SW) - collector-drainage water (rain and meltwater) - fact - mechanical treatment (CD/MEH) - plan - treatment (CD/MECH/BIO) 6. Access to sanitation (connection of the population to the SSS (%) number of subscribers (population) of the territorial community (TC) - actual - 100%/70.546 thousand people - plan - 100%/70.546 thousand people 7. Climate neutrality - actual - use of outdated equipment - plan - replacement of equipment, use of energy-saving pumping equipment | PJSC "ICCC" | no |  | 70.5 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Izmail TG | Stepovyi sleeve | UA_M5.3.4_0007 | At risk |  |  | missing | + | [5 empty] | 52.9 | [5 empty] | 24 | 1269.828 |  |  | 1269.828 | 2022 | The Drinking Water of Ukraine programme, regional and oblast programmes for socio-economic development of the community | State, local budgets, other budgets not prohibited by law | Izmail TG | 2025-2030 | 1 | The calculation is based on the cost of clean-up of BIOs of EUR 200 per person and TROs of EUR 250 per person at the NBU exchange rate of UAH 40. Total cost 70,546 x 450 x 40 = UAH 1269.828 million | Izmail District Military Administration, Black Sea and Lower Danube River Basin Management District | 2022 рік
8 | GWEP 4 |  | 8.1.4 |  | Cleaning and deepening the channel of the Dunayets River Kiliya TG Izmail district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); - Improving stream continuity for biota migration, etc. | Implementation of channel cleaning works, reduction of reed beds with a length of 13.2 km, approximate volume of silt removed 27.72 thousand m3. Google coordinates of the restoration area: 45.443547, 29.349659 to 45.455621, 29.498638 | Kiliya TG | no |  | 33.7 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Kiliya TG | Solomon sleeve | UA_М5.3.4_0012 | At risk | Failure to achieve the good |  | Danube Biosphere Reserve of national importance |  |  | + | [5 empty] | 13.2 |  |  |  | 2.5 | 33 |  |  | 33 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Kiliya TG | 2025-2030 | 2 | No design project, estimates are approximate | Kiliya TG | 2023
9 | GWP 1, GWP 2, GWP 3 |  | 8.1.1., 8.1.2., 8.1.3. |  | Construction of sewage treatment plants and sewerage networks in the city of Reni. Reni Reni TG Izmail district, Odesa region | General (mandatory) data on the CSP operator: 1. Balance sheet holder: Municipal enterprise "Vodokanal" of the Reni City Council 2. EDRPOU code: 36881597 3. Water user code: 510720 4. Information on the operation of the WSS (as of 01.01.2023) Waste water discharged per year, million cubic metres - total: 0.266 - without treatment: 0 - insufficiently treated: 0 - normatively clean (without purification): 0 - normatively treated at treatment plants: 0 - biological treatment: 0 - physical and chemical treatment: 0 - mechanical: 0 - capacity of treatment facilities, after which waste water is discharged into water bodies: 0 including those that provide regulatory treatment: capacity of treatment facilities, after which the return (waste) water is discharged to irrigation fields, terrain, filtration fields, storage tanks and cesspools: 0 | 1. Number of sewage treatment systems (STS) - actual / plan : 0/1 2. Method of waste water treatment - actual - 0 (not available) - plan - MECH(1)/BIO(2)/TRO(3) 3. Capacity of facilities after which wastewater is discharged to the surface water body (SWB) - actual - 0 (not available) - plan - 6.42 thousand m³/day (2.343 million m³/year) 4. Residual sediment (sludge) - actual - 0 (absent) - plan - treatment (partial recycling) 5. Stormwater drainage (SW) - collector-drainage water (rain and melt) - actual - mechanical treatment (CD/MEH) - plan - treatment (CD/MECH/BIO) 6. Access to sanitation (connection of the population to the SSS (%) number of subscribers (population) of the territorial community (TC) - actual - 46%/9.97 thousand people - plan - 100%/21.4 thousand people 7. Climate neutrality - actual - use of outdated equipment - plan - replacement of equipment, use of energy-saving pumping equipment | Municipal enterprise "Vodokanal" of the Reni City Council | no |  | 21.4 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Reni TG | Cahul Lake | UA_M5.3.4_0018 | No risk | Failure to achieve the good |  | missing | + | [5 empty] | 6.42 | [5 empty] | 60 | 385.2 |  |  | 385.2 | 2022 | The Drinking Water of Ukraine programme, regional and oblast programmes for socio-economic development of the community | State, local budgets, other budgets not prohibited by law | Reniyska AH | 2025-2030 | 1 | Calculated as of 30.07.2017. The calculation is based on the estimated cost of clean-up of BIOs of EUR 200 per person and TROs of EUR 250 per person at the NBU exchange rate of UAH 40. Total cost 21.4 x 450 x 40 = UAH 385.2 million | EYDAP SA and Odesa Regional Council | 2022 рік
10 | GWEP 4 |  | 8.1.4 |  | Clearing vegetation and silt from the Dandor pond Krynychnenska TG, Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Carrying out channel cleaning works, reducing the area of reeds. The area is 16.7 hectares, the approximate volume of silt removed is 47 thousand m3. Google coordinates of the site 45.531153, 28.704450 | Krynychnenska TG | no |  | 4.4 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Krynychnenska TG | Yalpug Lake SWPPP | UA_M5.3.4_0024 | No risk | Failure to achieve the good |  | missing |  |  | + | [6 empty] | 16.7 |  |  | 0.7 | 11.69 |  |  | 11.69 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Krynychnenska TG | 2025-2030 | 2 | No design project, estimates are approximate | Krynychnenska TG | 2023
11 | GWEP 4 |  | 8.1.4 |  | Revitalisation of the Karasulak River Vasylivska TG, Kubeyska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); | The length of the restoration area is 22.05 km Google coordinates of the restoration area are 45.831411, 28.780662 to 45.580381, 28.685713; Total volume of bottom sediments - 35.7 thousandm3 | Kubeyska TG, Bolhradska TG, Vasylivska TG | no |  | 21.1 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Vasylivska TG | Karasulak River IBA, Karasulak River IBA | UA_M5.3.4_0027, UA_M5.3.4_0029 | At risk | Failure to achieve good UA_M5.3.4_0029 |  | Within Kubeyskaya TG (Krasnoarmeyskiy arboretum) of local significance, within Vasylivska TG - Zhovtnevyi entomological reserve of local significance |  |  | + | [5 empty] | 22.05 |  |  |  | 3.5 | 77.175 |  |  | 77.175 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Kubeyska TG, Vasylivska TG | 2025-2030 | 1 | No design project, estimates are approximate | Kubeyska TG, Vasylivska TG | 2023
12 | GWEP 4 |  | 8.1.4 |  | Cleaning up the Karasulske reservoir Kubeyska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of the reservoir bed to improve the hydrological condition: Kasulske reservoir, area 55 ha, volume of silt removed 550 thousand m3. Google coordinates of the restoration site 45.732736, 28.718075 | Kuban TG | no |  | 9.6 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Kuban TG | Karasulske water reservoir | UA_M5.3.4_0028 | At risk |  |  | missing |  |  |  | + | [5 empty] | 55 |  |  | 0.7 | 38.5 |  |  | 38.5 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Kuban TG | 2025-2030 | 2 | No design project, estimates are approximate | Kuban TG | 2023
13 | GWEP 4 |  | 8.1.4 |  | Revitalisation of the Karasulak River Krynychnenska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); - management of hydraulic structures (environmentally adapted operation of hydraulic structures); - Improving flow continuity for biota migration, etc.Removal of barriers in the Karasulak River channel that disrupt the continuity of water flow and h | The length of the restoration area is 6.988 km Google coordinates of the restoration area from 45.580348, 28.685489 to 45.519859, 28.661348; Total volume of sediments - 82.484 thousandm3 The works include: extraction of sediments: including: 40.199 thousand m3 by dredger, 42.285 thousand m3 by dragline excavator | Krynychnenska TG | no |  | 4.4 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Krynychnenska TG | Karasulak River IWRM | UA_M5.3.4_0029 | At risk | Failure to achieve the good |  | missing |  |  | + | [5 empty] | 7 |  |  |  | 2.69 | 18.842 |  |  | 18.842 | 2021 | Work project "Cleaning up the Karasulak River in the territory of Krynychne Village Council, Bolhrad District, Odesa Region" 2021 р. | Regional and local budgets, other funds not prohibited by law | Krynychnenska TG | 2025-2030 | 1 |  | Krynychnenska TG | 2023
14 | GWEP 4 |  | 8.1.4 |  | Clearing of internal gullies of Staronekrasivski floodplains Safianivska TG, Izmail district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of internal gullies of Staronekrasivski floodplains to improve the hydrological condition: the total length is 19.2 km, the estimated volume of silt removed is 13.4 thousand m3. Google coordinates of the restoration area 45.373463,28.965681 | Safianivska TG | no |  | 43.1 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Safianivska TG | Lung Lake | UA_M5.3.4_0035 | At risk |  |  | Lung Landscape Reserve |  |  | + | [5 empty] | 19.2 |  |  |  | 2.5 | 48 |  |  | 48 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Safianivska TG | 2025-2030 | 2 | No design project, estimates are approximate | The Black Sea and lower Danube rivers | 2023
15 | GWEP 4 |  | 8.1.4 |  | Clearing the channel of the Malyi Katlabukh River Suvorovskaya TG Izmail district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); - Improving stream continuity for biota migration, etc. | Implementation of channel cleaning works, reduction of reed beds Length of the river within the Suvorivska territorial community is 7.8 km, approximate volume of silt removed is 19.7 thousand m3. approximate area of reed clearing is 20 hectares. Google coordinates of the restoration area from 45.652513, 28.961833 to 45.599922, 28.955989 | Suvorovskaya TG | no |  | 11.9 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Suvorovskaya TG | Small Katlabukh River IWRM | UA_М5.3.4_0054 | At risk |  |  | missing |  |  | + | [5 empty] | 7.8 |  |  |  | 2.5 | 19.5 |  |  | 19.5 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Suvorovskaya TG | 2025-2030 | 2 | No design project, estimates are approximate | Suvorovskaya TG | 2023
16 | GWEP 4 |  | 8.1.4 |  | Cleaning and deepening the channel of the Kirgiz-China River Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); - Improving stream continuity for biota migration, etc. | Clearing the riverbed of excessive vegetation and silt with the obligatory preservation of the natural morphological characteristics of the riverbed and banks for a length of 21.39 km, with an estimated volume of silt removed of 25,668 m3. Google coordinates of the restoration area are 46.122351, 28.983156 to 45.948523, 29.059087 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | Kirgiz River, Kirgiz River, Kirgiz River | UA_М5.3.4_0064, UA_М5.3.4_0066 | At risk |  |  | missing |  |  | + | [5 empty] | 21.4 |  |  |  | 2.5 | 53.48 |  |  | 53.48 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
17 | GWEP 4 |  | 8.1.4 |  | Cleaning of water bodies Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of the reservoir bed to improve the hydrological condition: Vilne village, Vilne Reservoir, area 72.0114 ha, approximate volume of silt removed 432.1 thousand m3. Google coordinates of the restoration site: 46.007007, 29.052498 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | Volninskoye water reservoir | UA_M5.3.4_0065 | At risk |  |  | missing |  |  |  | + | [5 empty] | 72 |  |  | 0.7 | 50.4 |  |  | 50.4 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
18 | GWEP 4 |  | 8.1.4 |  | Cleaning of water bodies Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of the pond bed to improve the hydrological condition: Maloyaroslavets village Second pond No. 2, area 3.5 ha, approximate volume of silt removed 21.0 thousand m3 . Google coordinates of the restoration site 46.138923, 29.089960 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | Kirgiz River | UA_М5.3.4_0072 | Possibly at risk |  |  | missing |  |  |  | + | [5 empty] | 3.5 |  |  | 0.7 | 2.45 |  |  | 2.45 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
19 | GWEP 4 |  | 8.1.4 |  | Cleaning of water bodies Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of the pond bed to improve the hydrological condition: Maloyaroslavets village Second pond No. 3, area 2.8 ha, approximate volume of silt removed 16.8 thousand m3; Google coordinates of the restoration site 46.128335, 29.092234 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | Kirgiz River | UA_М5.3.4_0072 | Possibly at risk |  |  | missing |  |  |  | + | [5 empty] | 2.8 |  |  | 0.5 | 1.4 |  |  | 1.4 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
20 | GWEP 4 |  | 8.1.4 |  | Cleaning of water bodies Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of the pond bed to improve the hydrological condition: Tvardychansky pond, area 9.2 hectares, approximate volume of silt removed 55.2 thousand m3. Google coordinates of the restoration site: 46.130276, 29.070805 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | Kirgiz River | UA_M5.3.4_0072 | Possibly at risk |  |  | missing |  |  |  | + | [5 empty] | 9.2 |  |  | 0.7 | 6.44 |  |  | 6.44 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
21 | GWEP 4 |  | 8.1.4 |  | Cleaning and deepening the channel of the Kyrgyzh River Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); - Improving stream continuity for biota migration, etc. | Clearing of the riverbed and water bodies from excessive vegetation and silt with the obligatory preservation of the natural morphological characteristics of the riverbed and banks for a length of 25.34 km, with an estimated volume of silt removed of 38.01 m3. Google coordinates of the restoration area are from 46.195311, 29.066796 to 45.983759, 29.137505 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | Kirgiz River, Kirgiz River | UA_М5.3.4_0072, UA_М5.3.4_0074 | At risk |  |  | missing |  |  | + | [5 empty] | 25.3 |  |  |  | 2.5 | 63.35 |  |  | 63.35 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
22 | GWEP 4 |  | 8.1.4 |  | Cleaning of water bodies Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of the pond bed to improve the hydrological condition: Vynohradivka village, pond No. 3, area 9.2 ha, approximate volume of silt removed 55.2 thousand m3. Google coordinates of the restoration site 46.127397, 29.130642 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | Vynogradivske water reservoir | UA_M5.3.4_0073 | At risk |  |  | missing |  |  |  | + | [5 empty] | 9.2 |  |  | 0.7 | 6.44 |  |  | 6.44 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
23 | GWEP 4 |  | 8.1.4 |  | Cleaning of water bodies Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of water bodies to improve their hydrological condition: Gulmen pond in Yarove village, area 27.5 ha, volume of silt removed 165.0 thousand m3. Google coordinates of the restoration site 46.0650328, 29.086726 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | EHIC Untitled | UA_М5.3.4_0078 | At risk |  |  | missing |  |  |  | + | [5 empty] | 27.5 |  |  | 0.7 | 19.25 |  |  | 19.25 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
24 | GWEP 4 |  | 8.1.4 |  | Cleaning of water bodies Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of a water body: - sediment management (extraction of bottom sediments); - removal of aquatic vegetation | Cleaning of water bodies to improve their hydrological condition: pond in Rivne village, area 15.2 ha, approximate volume of silt removed 91.2 thousand m3. Google coordinates of the restoration site: 46.011730, 29.159995 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | EHIC Untitled | UA_М5.3.4_0078 | At risk |  |  | missing |  |  |  | + | [5 empty] | 15.2 |  |  | 0.7 | 10.64 |  |  | 10.64 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
25 | GWEP 4 |  | 8.1.4 |  | Cleaning and deepening of the Aliyaga riverbed Tarutynska TG Bolhradskyi district, Odesa region | Carrying out a set of measures to restore (improve) the hydromophological characteristics of the watercourse: - sediment management (extraction of bottom sediments); - Improving stream continuity for biota migration, etc. | The works are aimed at clearing the riverbed from excessive vegetation and silt with the obligatory preservation of the natural morphological characteristics of the riverbed and banks, 26.72 km long, with an estimated volume of 41.683 thousand m3 of silt removed. Google coordinates of the restoration area are 46.195986, 29.098025 to 45.987687, 29.217946 | Tarutino TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bolgradsky | Tarutino TG | The Aliyaga river is an IBA, Aliyaga River IBA | UA_М5.3.4_0079, UA_М5.3.4_0080 | At risk |  |  | missing |  |  | + | [5 empty] | 41.7 |  |  |  | 2.5 | 66.8 |  |  | 66.8 | 2022 |  | Regional and local budgets, other funds not prohibited by law | Tarutino TG | 2025-2030 | 2 | No design project, estimates are approximate | Tarutino TG | 2023
1 | GWP 1, GWP 2, GWP 3, GWP 4 |  | 8.1.1., 8.1.2., 8.1.3., 8.1.4, 8.2.1.1, 8.2.2. |  | Economic and environmental certification of water users in the Lower Danube sub-basin on the basis of digitalisation 16 TG Bilhorod-Dnistrovskyi rayon, Bolhradskyi rayon, Izmailskyi rayon Odesa oblast | Development of a concept and mechanism for the introduction of economic and environmental certification of water users in the Lower Danube sub-basin based on digital transformation | Determination of restrictions and burdens on water management activities and development of scientifically based indicators and forms of economic and environmental passports for water users in the Lower Danube sub-basin using digital technologies | Tatarbunary TG, Krynychne TG, Vasylivka TG, Pavlivka TG, Bolhrad TG, Artsyz TG, Tarutino TG, Teplyk TG, Kubey TG, Horodne TG, Vilkovo TG, Suvorove TG, Safianivka TG, Reni TG, Kiliya TG, Izmail TG | no |  | 350 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bilhorod-Dnistrovskyi, Bolgradskyi, Izmailskyi | Tatarbunary TG, Krynychne TG, Vasylivka TG, Pavlivka TG, Bolhrad TG, Artsyz TG, Tarutino TG, Teplyk TG, Kubey TG, Horodne TG, Vilkovo TG, Suvorove TG, Safianivka TG, Reni TG, Kiliya TG, Izmail TG | Danube River, Kislicki arm, Ivanesti arm, Tataru mouth, Stepovyi arm, Katenka arm, Mashenka arm, Laptish mouth, Murza mouth, Solomonov arm, Belgorodske mouth, Ochakivske mouth, Prorva mouth, IZMV No name, IZMV No name, Viketa stream, IZMV connecting channel of Lake Kart. Kart, Yalpukh River, Bolshaya Salcha River, Skunda River, Karasulak River, Kugu Lake IWRM connecting channel, Kairakliya River, Kairakliya Lake IWRM connecting channel, Lung Lake IWRM connecting channel. Lung, Tashbunar River, Bolshoy Katlabukh River, Bolshoy Katlabukh River, Maly Katlabukh River, Maly Katlabukh River, Yenika River, Yenika River, Zhelyavsky Connecting Canal, Kirgiz-China River, Kirgiz-China River, No name, Valeperzha river, Valeperzha river, Kirgiz river, Kirgiz river, Kirgiz river, No name, Aliyaga river, Tashlyk river, Tashlyk river, Kofa canal, Drakulya river, Drakulya river, Nerushai river, Nerushai river | UA_M5.3.4_0001, UA_M5.3.4_0002, UA_M5.3.4_0003, UA_M5.3.4_0004, UA_M5.3.4_0005, UA_M5.3.4_0006, UA_M5.3.4_0007, UA_M5.3.4_0008, UA_M5.3.4_0009, UA_M5.3.4_0010, UA_M5.3.4_0011, UA_M5.3.4_0012, UA_M5.3.4_0013, UA_M5.3.4_0014, UA_M5.3.4_0015, UA_M5.3.4_0016, UA_M5.3.4_0017, UA_M5.3.4_0019, UA_M5.3.4_0021, UA_M5.3.4_0022, UA_M5.3.4_0023, UA_M5.3.4_0026, UA_M5.3.4_0027, UA_M5.3.4_0029, UA_M5.3.4_0030, UA_M5.3.4_0031, UA_M5.3.4_0033, UA_M5.3.4_0036, UA_M5.3.4_0037, UA_M5.3.4_0039, UA_M5.3.4_0040, UA_M5.3.4_0042, UA_M5.3.4_0043, UA_M5.3.4_0045, UA_M5.3.4_0046, UA_M5.3.4_0048, UA_M5.3.4_0049, UA_M5.3.4_0050, UA_M5.3.4_0051, UA_M5.3.4_0052, UA_M5.3.4_0054, UA_M5.3.4_0055, UA_M5.3.4_0056, UA_M5.3.4_0057, UA_M5.3.4_0058, UA_M5.3.4_0060, UA_M5.3.4_0062, UA_M5.3.4_0063, UA_M5.3.4_0064, UA_M5.3.4_0066, UA_M5.3.4_0067, UA_M5.3.4_0068, UA_M5.3.4_0069, UA_M5.3.4_0071, UA_M5.3.4_0072, UA_M5.3.4_0074, UA_M5.3.4_0075, UA_M5.3.4_0077, UA_M5.3.4_0078, UA_M5.3.4_0079, UA_M5.3.4_0080, UA_M5.3.4_0081, UA_M5.3.4_0082, UA_M5.3.4_0083, UA_M5.3.4_0085, UA_M5.3.4_0087, UA_M5.3.4_0088, UA_M5.3.4_0090, UA_M5.3.4_0091, UA_M5.3.4_0093 | At risk / Possibly at risk | Недосягнення доброго UA_M5.3.4_0001 UA_M5.3.4_0003 UA_M5.3.4_0004 UA_M5.3.4_0012 UA_M5.3.4_0023 UA_M5.3.4_0029 |  | Danube Biosphere Reserve of national importance, Regional Landscape Park of local importance "Izmail Islands", Landscape Reserve of national importance "Lake Kartal", Landscape Reserve of local importance "Lung" | [5 empty] | + | [6 empty] | 5.2 | 5.2 |  |  | 5.2 | 2023 | Recovery Plan of Ukraine, Drinking Water of Ukraine Programme, strategies for socio-economic development of the region and communities, EU Strategy for the Danube Region | State, regional, local budgets, other not prohibited by law | Odesa Regional State Administration, with the scientific support of the State Institution "IREED of the National Academy of Sciences of Ukraine" | 2025-2027 | 1 | The event is planned in accordance with the EU Directives, in particular, 91/271/EEC, 98/83/EC, 91/676/EC, 2003/35/EC, 2008/98/EC and in accordance with other EU Directives specified in the Methodology | State Institution "IREED of the National Academy of Sciences of Ukraine" | 2023
2 | GWP 1, GWP 2, GWP 3, GWP 4 |  | 8.1.1., 8.1.2., 8.1.3., 8.1.4, 8.2.1.1, 8.2.2. |  | Development of a Strategy for the greening of water management activities in the context of sustainable development of the Lower Danube sub-basin 16 TG Bilhorod-Dnistrovskyi rayon, Bolhradskyi rayon, Izmailskyi rayon Odesa oblast | Formulation of proposals for the definition of strategic priorities, organisational and economic mechanisms, measures aimed at reducing water pollution by organic, nutrient and hazardous substances (diffuse and point sources) for territorial communities (16 communities) in the Lower Danube sub-basin | Identification of scientifically sound goals, objectives, organisational and economic instruments for the implementation of measures aimed at reducing water pollution by organic, nutrient and hazardous substances (diffuse and point sources) for territorial communities in the Lower Danube sub-basin (16 TGs) | Tatarbunary TG, Krynychne TG, Vasylivka TG, Pavlivka TG, Bolhrad TG, Artsyz TG, Tarutino TG, Teplyk TG, Kubey TG, Horodnya TG, Vilkovo TG, Suvorove TG, Safianivka TG, Reni TG, Kiliya TG, Izmail TG | no |  | 350 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Bilhorod-Dnistrovskyi, Bolgradskyi, Izmailskyi | Tatarbunary TG, Krynychne TG, Vasylivka TG, Pavlivka TG, Bolhrad TG, Artsyz TG, Tarutino TG, Teplyk TG, Kubey TG, Horodnya TG, Vilkovo TG, Suvorove TG, Safianivka TG, Reni TG, Kiliya TG, Izmail TG | Danube River, Kislicki arm, Ivanesti arm, Tataru mouth, Stepovyi arm, Katenka arm, Mashenka arm, Laptish mouth, Murza mouth, Solomonov arm, Belgorodske mouth, Ochakivske mouth, Prorva mouth, IZMV No name, IZMV No name, Viketa stream, IZMV connecting channel of Lake Kart. Kart, Yalpukh River, Bolshaya Salcha River, Skunda River, Karasulak River, Kugu Lake IWRM connecting channel, Kairakliya River, Kairakliya Lake IWRM connecting channel, Lung Lake IWRM connecting channel. Lung, Tashbunar River, Bolshoy Katlabukh River, Bolshoy Katlabukh River, Maly Katlabukh River, Maly Katlabukh River, Yenika River, Yenika River, Zhelyavsky Connecting Canal, Kirgiz-China River, Kirgiz-China River, No name, Valeperzha river, Valeperzha river, Kirgiz river, Kirgiz river, Kirgiz river, No name, Aliyaga river, Tashlyk river, Tashlyk river, Kofa canal, Drakulya river, Drakulya river, Nerushai river, Nerushai river | UA_M5.3.4_0001, UA_M5.3.4_0002, UA_M5.3.4_0003, UA_M5.3.4_0004, UA_M5.3.4_0005, UA_M5.3.4_0006, UA_M5.3.4_0007, UA_M5.3.4_0008, UA_M5.3.4_0009, UA_M5.3.4_0010, UA_M5.3.4_0011, UA_M5.3.4_0012, UA_M5.3.4_0013, UA_M5.3.4_0014, UA_M5.3.4_0015, UA_M5.3.4_0016, UA_M5.3.4_0017, UA_M5.3.4_0019, UA_M5.3.4_0021, UA_M5.3.4_0022, UA_M5.3.4_0023, UA_M5.3.4_0026, UA_M5.3.4_0027, UA_M5.3.4_0029, UA_M5.3.4_0030, UA_M5.3.4_0031, UA_M5.3.4_0033, UA_M5.3.4_0036, UA_M5.3.4_0037, UA_M5.3.4_0039, UA_M5.3.4_0040, UA_M5.3.4_0042, UA_M5.3.4_0043, UA_M5.3.4_0045, UA_M5.3.4_0046, UA_M5.3.4_0048, UA_M5.3.4_0049, UA_M5.3.4_0050, UA_M5.3.4_0051, UA_M5.3.4_0052, UA_M5.3.4_0054, UA_M5.3.4_0055, UA_M5.3.4_0056, UA_M5.3.4_0057, UA_M5.3.4_0058, UA_M5.3.4_0060, UA_M5.3.4_0062, UA_M5.3.4_0063, UA_M5.3.4_0064, UA_M5.3.4_0066, UA_M5.3.4_0067, UA_M5.3.4_0068, UA_M5.3.4_0069, UA_M5.3.4_0071, UA_M5.3.4_0072, UA_M5.3.4_0074, UA_M5.3.4_0075, UA_M5.3.4_0077, UA_M5.3.4_0078, UA_M5.3.4_0079, UA_M5.3.4_0080, UA_M5.3.4_0081, UA_M5.3.4_0082, UA_M5.3.4_0083, UA_M5.3.4_0085, UA_M5.3.4_0087, UA_M5.3.4_0088, UA_M5.3.4_0090, UA_M5.3.4_0091, UA_M5.3.4_0093 | At risk / Possibly at risk | Недосягнення доброго UA_M5.3.4_0001 UA_M5.3.4_0003 UA_M5.3.4_0004 UA_M5.3.4_0012 UA_M5.3.4_0023 UA_M5.3.4_0029 |  | Danube Biosphere Reserve of national importance, Regional Landscape Park of local importance "Izmail Islands", Landscape Reserve of national importance "Lake Kartal", Landscape Reserve of local importance "Lung" | [5 empty] | + | [6 empty] | 9.6 | 9.6 |  |  | 9.6 | 2023 | Recovery Plan of Ukraine, Drinking Water of Ukraine Programme, strategies for socio-economic development of the region and communities, EU Strategy for the Danube Region | State, regional, local budgets, other not prohibited by law | State Institution "IREED of the National Academy of Sciences of Ukraine" | 2025-2028 | 1 | The event is planned in accordance with EU Directives, in particular, 91/271/EEC, 98/83/EC, 91/676/EEC, 2003/35/EC and in accordance with other EU Directives specified in the Methodology | State Institution "IREED of the National Academy of Sciences of Ukraine" | 2023
3 | GWEP 4 |  | 8.1.4 |  | Modernisation of the hydrological infrastructure management system and hydrological monitoring of water management systems "Kyslytskyi arm of the Stepovyi arm - floodplain of the Stepovyi arm - Lake China" Safianivska TG, Izmail district, Odesa region | Work to improve remote control of water infrastructure and water environment monitoring | Installation of remote monitoring and control equipment for water facilities | Safianivska TG | no |  | 70 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Safianivska TG | Kyslytskyi arm, Lake Kita, Kofa canal | UA_M5.3.4_0004, UA_M5.3.4_0086, UA_M5.3.4_0087 | At risk |  |  | missing | [5 empty] | + | [6 empty] | 35 | 35 |  |  | 35 | 2023 | The Drinking Water of Ukraine programme, regional and oblast programmes of social and economic development of the community | State, local budgets, other budgets not prohibited by law | Izmail TG | 2025-2030 | 2 | State Institution "IREED of the National Academy of Sciences of Ukraine" | State Institution "IREED of the National Academy of Sciences of Ukraine" | 2023
4 | GWEP 4 |  | 8.1.4 |  | Modernisation of the hydrological infrastructure management and hydrological monitoring system of the Safiany - Katlabukh water management system Safianivska TG, Izmail district, Odesa region | Work to improve remote control of water infrastructure and water environment monitoring | Installation of remote monitoring and control equipment for water facilities | Safianivska TG | no |  | 23.91 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Safianivska TG | Kairaklia River, Lake Safyani | UA_M5.3.4_0033, UA_M5.3.4_0034 | At risk |  |  | missing | [5 empty] | + | [6 empty] | 40 | 40 |  |  | 40 | 2023 | The Drinking Water of Ukraine programme, regional and oblast programmes of social and economic development of the community | State, local budgets, other budgets not prohibited by law | Izmail TG | 2025-2030 | 2 | State Institution "IREED of the National Academy of Sciences of Ukraine" | State Institution "IREED of the National Academy of Sciences of Ukraine" | 2023
5 | GWEP 4 |  | 8.1.4 |  | Modernisation of the hydrological infrastructure management system and hydrological monitoring of water management systems "Kyslytskyi Rukav - Staronekrasivski Plains - Lung Lakes" Izmail TG Izmail district, Odesa region | Work to improve remote control of water infrastructure and water environment monitoring | Installation of remote monitoring and control equipment for water facilities | Izmail TG | no |  | 70.1 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Izmail TG | Lake Lung connecting canal | UA_M5.3.4_0036 | At risk |  |  | Lung Landscape Reserve | [5 empty] | + | [6 empty] | 30 | 30 |  |  | 30 | 2023 | The Drinking Water of Ukraine programme, regional and oblast programmes of social and economic development of the community | State, local budgets, other budgets not prohibited by law | Izmail TG | 2025-2030 | 2 | State Institution "IREED of the National Academy of Sciences of Ukraine" | State Institution "IREED of the National Academy of Sciences of Ukraine" | 2023
6 | GWEP 4 |  | 8.1.4 |  | Modelling of water and salt balance and water quality in the Danube Lake Katlabukh, Safianivska TG, Izmail district, Odesa region | Substantiation of the structure of the equation of water and salt balance of Lake Katlabukh, the nature of interactions between its components in years of different water availability, and simulation modelling by scenarios. For the first time, it is planned to assess such a component of the water balance as surface water inflow (in the absence of flow observations on the rivers feeding the lake) not only by the methodology of its calculation, but also by the possibility of long-term forecasting of fresh surface water inflow to the lake in each year during the most high-water phase of the water regime of the Danube basin rivers - spring flood. | A methodology for determining the probability of recurrence of spring floods in a multi-year context was substantiated and implemented, which will make it possible to assess the degree of regulation of surface waters by the reservoir capacity during the passage of floods with a rare probability of exceeding ( P = 1%i.e., once every 100 years) | Safianivska TG | no |  | 43.1 | M5.3 Danube River Basin Region | M5.3.4 Lower Danube sub-basin | Odesa | Izmail | Safianivska TG | Lake Katlabukh | UA_M5.3.4_0061 | No risk |  |  | missing | [5 empty] | + | [6 empty] | 0.3 | 0.3 |  |  | 0.3 | 2023 | "The Danube Regional Programme 2021-2027, approved by the European Commission in November 2022. | State, local budgets, other budgets not prohibited by law | Safianivska TG | 2025-2030 | 1 |  | Odesa State Environmental University | 2023